## Development Plan
S.No. | Task | Application Can be implemented in Project | Status | Course Should be Completed by | Timelines | Duration in Hrs | time axis 2018-10-29 to 2019-10-21
1 | Tools |  |  |  | Planned | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 2 | 4 | 2 | 6 | 0 | 0 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Python (Implementation oF stats) | NUMPY/PANDAS Fridy session(Late night videos) | Planned |  | Planned | 20 | 2018-12-17: 5; 2018-12-24: 5; 2019-01-07: 2; 2019-01-14: 2; 2019-02-04: 4; 2019-02-18: 2; 2019-02-25: 4; 2019-03-04: 2; 2019-03-11: 6; 2019-04-01: 2; 2019-04-08: 2; 2019-04-15: 6
[5 empty] | Actual | 0
1.4 | R Programming( (Implementation oF stats) |  | Planned |  | Planned | 0
[5 empty] | Actual | 0
2 | Basic Statistics & ML concepts |  |  |  | Planned | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 16 | 18 | 2 | 0 | 0 | 6 | 10 | 6 | 10 | 10 | 6 | 10
[5 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | EDA(Exploratory data analysis) |  | Planned |  | Planned | 0 | 2019-03-25: 4; 2019-04-01: 10
[5 empty] | Actual | 14 | 2019-03-25: 4; 2019-04-01: 10
2.2 | Probability & Stats concepts(Distribution Types) | Recon analysis (uhn) | Planned |  | Planned | 0 | 2019-03-25: 4
[5 empty] | Actual | 4 | 2019-03-25: 4
2.3 | Correlation | Addition To GRIP(How difft business can be Impacted together) | Planned |  | Planned | 0
[5 empty] | Actual | 0
2.3 | Dimensinaly reduction types |  | Planned |  | Planned | 0 | 2019-04-08: 4; 2019-04-15: 6
[5 empty] | Actual | 0
2.4 | Classification & regression Models(KNN-RAT) | RAT Tool Further study | Planned |  | Planned | 0 | 2019-05-13: 6; 2019-05-20: 10; 2019-05-27: 6
[5 empty] | Actual | 0
2.3 | Logistic Regression |  | Planned |  | Planned | 0 | 2019-06-03: 10; 2019-06-10: 10
[5 empty] | Actual | 0
2.4 | Linear Regression |  | Planned |  | Planned | 0 | 2019-06-17: 6; 2019-06-24: 10; 2019-07-01: 4
[5 empty] | Actual | 0
2.2 | Decision Trees |  | Planned |  | Planned | 0 | 2019-04-01: 10; 2019-04-08: 2; 2019-04-15: 2; 2019-07-08: 10; 2019-07-15: 10
[5 empty] | Actual | 0
2.5 | Ensemble Models (Random Forest, XGBoost, AdaBoost) |  | Planned |  | Planned | 0 | 2019-04-08: 10; 2019-04-15: 10; 2019-04-22: 2; 2019-07-22: 10; 2019-07-29: 10; 2019-08-05: 4
[5 empty] | Actual | 0
2.6 | Unsupervised learning (Clustering etc) |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
2.7 | Clustering Techniques |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
2.8 | Neural Networks |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
3 | Analytical Fundamentals |  |  |  | Planned | 0
[5 empty] | Actual | 0
3.1 | Frameworks |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
3.2 | Problem Solving approach |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
4 | Business/Domain Knowledge |  |  |  | Planned | 0 | 2018-10-29: 0; 2018-11-05: 0; 2018-11-12: 0; 2018-11-19: 0; 2018-11-26: 0; 2018-12-03: 0; 2018-12-10: 0; 2018-12-17: 0; 2018-12-24: 0; 2018-12-31: 0; 2019-01-07: 0; 2019-01-14: 0; 2019-01-21: 0; 2019-01-28: 0; 2019-02-04: 0; 2019-02-11: 0; 2019-02-18: 0
[5 empty] | Actual | 0 | 2018-10-29: 0; 2018-11-05: 0; 2018-11-12: 0; 2018-11-19: 0; 2018-11-26: 0; 2018-12-03: 0; 2018-12-10: 0; 2018-12-17: 0; 2018-12-24: 0; 2018-12-31: 0; 2019-01-07: 0; 2019-01-14: 0; 2019-01-21: 0; 2019-01-28: 0; 2019-02-04: 0; 2019-02-11: 0; 2019-02-18: 0
4.1 | HealthCare - AHM250 |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0
4.2 | Affordable Care Act - Changes / Key Points |  | Not Planned |  | Planned | 0
[5 empty] | Actual | 0